## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Going through Creative Brief | Research |  | 2 | 1 | -1 |  | Creative brief shorter than i expected.
| Done | Max 4 hours tasks | Kick-off | Lecture |  | 1 | 1 | 0
| Done | Max 4 hours tasks | Going deeper into study materials and Creative brief | Research |  | 2 | 2 | 0 |  | Everything is well explained and clear for now
| Done | Max 4 hours tasks | Completing a survey with sentences with my emotions | Study |  | 1 | 1 | 0
| Done | Max 4 hours tasks | Week 1 Self study: Linguistics | Study |  | 2 | 2.5 | 0.5
| Done | Max 4 hours tasks | Searching for ideas for smart goals | Research |  | 1 | 0.75 | -0.25 |  | I have 2 smarter goals (checklist and linkedin account) now i have to describe them in learning log
| Done | Max 4 hours tasks | Reading: Chapter 2 Regular Expressions, Text Normalization, Edit Distance | Study |  | 2 | 3 | 1 |  | Its hard to learn from reading i prefer courses and videos and practise skills in notebooks is the best option
| Done | Max 4 hours tasks | CH1 Section 1/Computing with Language: Texts and Words | Study |  | 1 | 1.5 | 0.5 |  | With chatbot explaining my some parts of the text is way easier
| Done | Max 4 hours tasks | CH1 Section 2/A Closer Look at Python: Texts as Lists of Words | Study |  | 1.5 | 1.5 | 0
| Done | Max 4 hours tasks | CH1 Section 3/Computing with Language: Simple Statistics | Study |  | 1.5 | 1.5 | 0
| Done | Max 4 hours tasks | CH1 Section 4/Back to Python: Making Decisions and Taking Control | Study |  | 1.5 | 1 | -0.5
| Done | Max 4 hours tasks | SH1 Section 5/Automatic Natural Language Understanding | Study |  | 1 | 1 | 0
| Done | Max 4 hours tasks | Introduction to Natural Language Processing in Python course | Study |  | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Introduction%20to%20Natural%20Language%20Processing.pdf
| Done | Max 4 hours tasks | Familiarizing myself with the data | Research |  | 2 | 2 | 0
| Done | Max 4 hours tasks | Downloading datasets | Programming |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Datasets/goemotions_dataset.csv
| Done | Max 4 hours tasks | Preprocesing datasets | Programming | ILO 4.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Datasets/preprocesing.ipynb
| Done | Max 4 hours tasks | Merging datasets | Programming |  | 1 | 1.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Datasets/emotion_data_merged.csv
| Done | Max 4 hours tasks | Task 1 | Study | ILO 4.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Notebooks/W1-DL1-Regular-Expressions-Student-Notebook.ipynb
| Done | Max 4 hours tasks | Task 2 | Study | ILO 4.1 | 2 | 2 | 0
| Done | Max 4 hours tasks | I also compleated a QUIZ | Evidencing | ILO 4.1 | 0.25 | 0.25 | 0 |  | i got 9/10 points
| Done | Max 4 hours tasks | I started working on my smart goal (Linkedin acount) | Study |  | 2 | 2 | 0 |  | I adjust streamlit dashboar and now everyone can open our project by cliking this link: https://projects-2024-2025-vje3z2mwxy42cxtjbt7ebm.streamlit.app/
| Done | Max 4 hours tasks | I created new git hub repository for projects from year 2 and i after adjustments i add project from Block A there | Design |  | 4 | 4 | 0 | https://github.com/DominikSzewczyk224180/Projects-2023-2024
| Done | Max 4 hours tasks | I add the decripon and whole project to my linkedin acount | Evidencing |  | 4 | 3.75 | -0.25 | https://www.linkedin.com/in/dominik-szewczyk/
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 41.75 | 42.25 | 0.5
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Self-study: Week 2: Data Processing | Study |  | 2 | 2 | 0
| Done | Max 4 hours tasks | Reading: Speech and Language Processing | Study |  | 3 | 3 | 0
| Done | Max 4 hours tasks | Reading: Papers | Study |  | 4 | 3.5 | -0.5 |  | With chatbot explaining my some parts of the text is way easier
| Done | Max 4 hours tasks | Course on DataCamp about SpaCy | Study |  | 5 | 5 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Self-study | I decided to finish all cours insted of 3 parts
| Done | Max 4 hours tasks | Familiarizing myself with taks 3 and task 7 | Study | ILO 4.1 | 2 | 2 | 0
| Done | Max 4 hours tasks | Preparing for the feedback Sesion | Evidencing | ILO 1.0 | 2 | 2.5 | 0.5
| Done | Max 4 hours tasks | I compleated week 2 QUIZ | Evidencing | ILO 4.1 | 0.25 | 0.25 | 0 |  | i got 9/10 points
| Done | Max 4 hours tasks | Task 4: Sentiment Extraction | Programming | ILO 4.1 | 3 | 3.5 | 0.5
| Done | Max 4 hours tasks | Task 7: Extract POS-tags | Programming | ILO 4.1 | 3 | 2.5 | -0.5 |  | I repeated the knowledge from the course
| Done | Max 4 hours tasks | I created simplified_emotions.csv | Programming | ILO 4.1 | 2 | 1.5 | -0.5
| Done | Max 4 hours tasks | I prepared my project from Block B for my git hub with projcts | Programming |  | 4 | 4 | 0 | https://github.com/DominikSzewczyk224180/Projects-2023-2024
| Done | Max 4 hours tasks | i add projct from block B to my Git hub account | Programming |  | 4 | 3.75 | -0.25 | https://www.linkedin.com/in/dominik-szewczyk/
| Done | Max 4 hours tasks | I add the decripon and whole project to my linkedin acount | Evidencing |  | 4 | 6 | 2 |  | It was challenging for me to write a proper description for the project
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 38.25 | 39.5 | 1.25
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Speech and Language Processing Chapter 4 Naive Bayes, Text Classification, and Sentiment | Study | ILO 4.1 | 3 | 2.75 | -0.25
| Done | Max 4 hours tasks | Speech and Language Processing Chapter 5 Logistic Regression | Study | ILO 4.1 | 3 | 3.25 | 0.25
| Done | Max 4 hours tasks | Naïve bayes and smoothing applications, Notebook 1 | Study | ILO 4.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Self-study/Notebooks
| Done | Max 4 hours tasks | Logistic regression, Notebook 2 | Study | ILO 4.2 | 3 | 3.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Self-study/Notebooks
| Done | Max 4 hours tasks | Apllaying extra featurest to the notebooks | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Self-study/Notebooks
| Done | Max 4 hours tasks | Task 4: Sentiment Extraction | Programming | ILO 4.1 | 2 | 2.25 | 0.25
| Done | Max 4 hours tasks | Task 9: Apply Naïve Bayes | Programming | ILO 4.2 | 4 | 4 | 0 |  | I used the knowledge I gained in the notebooks
| Done | Max 4 hours tasks | Workshops in teams on improving your presentation skills | Workshop |  | 1 | 1 | 0
| Done | Max 4 hours tasks | Week 9 - 10 Challenge presentation | Lecture | ILO 2.0 | 0.75 | 0.5 | -0.25
| Done | Max 4 hours tasks | Improving accuracy with extra features | Programming | ILO 1.0 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Na%C3%AFve%20Bayes | I already knew how to apply extra features
| Done | Max 4 hours tasks | Creating first submition to kaggle | Programming | ILO 5.0 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Na%C3%AFve%20Bayes | 80 % accuracy (not bad)
| Done | Max 4 hours tasks | Adjusting data sets | Programming |  | 3 | 3 | 0 |  | I add 2 new datasets
| Done | Max 4 hours tasks | Task 10: Apply Logistic Regression | Programming | ILO 4.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Logistic%20Regression
| Done | Max 4 hours tasks | Creating first submition to kaggle with logisic regresion | Programming | ILO 5.0 | 2 | 4 | 2 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Logistic%20Regression | I think I'm doing everything right, but the results are bad, and I still heave to work on that
| Done | Max 4 hours tasks | I created my CV ( i will u |  |  | 4 | 4 | 0 |  | I will use it when i am gonna look for internship
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 37.75 | 39.5 | 1.75
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Rewriting in logistic regression model | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Logistic%20Regression
| Done | Max 4 hours tasks | Workshop titled "Writing Intention Revealing Code" by Ekin Ocalan | Programming |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Notebooks/writing_intention_revealing_code.ipynb
| Done | Max 4 hours tasks | Team meeting | Meeting |  | 1 | 1 | 0 |  | We successfully discuss your goals and plans for the project
| Done | Max 4 hours tasks | Speech and Language Processing Chapter 6 Vector Semantics and Embeddings | Study |  | 4 | 4 | 0
| Done | Max 4 hours tasks | Speech and Language Processing Chapter 9 RNNs and LSTMs | Study |  | 4 | 4 | 0
| Done | Max 4 hours tasks | Logstic Regresion solving Error | Programming | ILO 4.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Logistic%20Regression | My model was predicting all emotions as other
| Done | Max 4 hours tasks | Logstic Regresion adjustments | Programming | ILO 1.0 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Logistic%20Regression
| Done | Max 4 hours tasks | W4-DL2-Embeddings-Student-Notebook.ipynb | Programming | ILO 4.1 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Notebooks/W4-DL2-Embeddings-Student-Notebook.ipynb
| Done | Max 4 hours tasks | Task 5: Implement Word Embeddings | Programming | ILO 4.1 | 2 | 1.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Word%20embeddings
| Done | Max 4 hours tasks | Task 8: Create Word Embeddings | Programming | ILO 4.1 | 3 | 2.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Word%20embeddings
| Done | Max 4 hours tasks | W5-DL1-RNNs-Student-Notebook.ipynb | Programming | ILO 4.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Notebooks/W5-DL1-RNNs-Student-Notebook.ipynb
| Done | Max 4 hours tasks | Task 11: Apply Statistical & Neural Models | Programming | ILO 4.2 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models
| Done | Max 4 hours tasks | Tryining to improve CNN model | Programming | ILO 4.2 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 34 | 34.5 | 0.5
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Speech and Language Processing Chapter 10 Transformers and Large Language Models | Study |  | 2 | 1 | -1 |  | I used chat bot to summarize some parts for me
| Done | Max 4 hours tasks | Speech and Language Processing Chapter 11 Fine-Tuning and Masked Language Models | Study |  | 2 | 1 | -1 |  | I used chat bot to summarize some parts for me
| Done | Max 4 hours tasks | Read the paper Attention Is All You Need by Vaswani | Study |  | 2 | 2 | 0
| Done | Max 4 hours tasks | Answering questions for the paper | Study |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Attention%20Is%20All%20You%20Need%20by%20Vaswani.md
| Done | Max 4 hours tasks | Lecture about peer feedback | Lecture |  | 0.5 | 0.5 | 0
| Done | Max 4 hours tasks | Lecture on cognitive models | Lecture |  | 2 | 2 | 0
| Done | Max 4 hours tasks | Creating a CNN model for group submision | Programming | ILO 4.2 | 3 | 3.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models/CNN_model_allemotions.ipynb | My score was realy low at the begining because i was using wrong test data
| Done | Max 4 hours tasks | Trying to creat a HMM model | Programming | ILO 4.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models/Hidden_Markov_Model.ipynb | It was harder than i expected
| Done | Max 4 hours tasks | Learning how to creat a HMM model | Study | ILO 4.2 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models/Hidden_Markov_Model.ipynb
| Done | Max 4 hours tasks | Creating HMM model | Programming | ILO 4.2 | 1 | 1.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models/Hidden_Markov_Model.ipynb
| Done | Max 4 hours tasks | Rewriting task 8 | Programming | ILO 4.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Word%20embeddings/Create_Word_Embeddings_Task8.ipynb | I found out that all my code disaper and i had to program it again
| Done | Max 4 hours tasks | Lecture on how to create a good presentation | Lecture | ILO 3.0 | 1 | 1 | 0
| Done | Max 4 hours tasks | Learning how to create Conditional Random Fields model | Study | ILO 4.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models/Conditional_Random_Fields.ipynb
| Done | Max 4 hours tasks | Creating Conditional Random Fields model | Programming | ILO 4.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models/Conditional_Random_Fields.ipynb
| Done | Max 4 hours tasks | Trying to improve HMM and CRF models performence | Programming | ILO 4.2 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models | It was harder than i expected
| Done | Max 4 hours tasks | Application of a recurrent neural network | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models
| Done | Max 4 hours tasks | Application of a Long Short-Term Memory (LSTM) | Programming | ILO 4.2 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models
| Done | Max 4 hours tasks | Submitting Quiz Week 5 | Evidencing | ILO 4.2 | 0.25 | 0.25 | 0
| Done | Max 4 hours tasks | Creating a Latex template for technical report | Design | ILO 6.0 | 1 | 1 | 0
| Done | Max 4 hours tasks | HuggingFace Course on using Transformers | Study | ILO 4.2 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Self-study/Notebooks/transformers-course.ipynb
| Done | Max 4 hours tasks | Learning how to create transformer learning in practise | Study | ILO 4.2 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/blob/main/Natural%20Language%20procesing/Transfer%20learning%20models/Learning_proces.ipynb
| Done | Max 4 hours tasks | Creating first transformer moel for indiidual chelenge | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transfer%20learning%20models
| Done | Max 4 hours tasks | Creating second transformer moel for indiidual chelenge | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transfer%20learning%20models
|  |  |  | Total Hours |  | 41.25 | 40.75 | -0.5
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Searching for different transformer models on Hugging Face | Research | ILO 4.2 | 1 | 1 | 0
| Done | Max 4 hours tasks | Team meeting | Meeting |  | 0.5 | 0.5 | 0 |  | We split task for Speech Recognition & Pipeline Building.
| Done | Max 4 hours tasks | Episodes into fragments | Programming | ILO 4.2 | 2 | 3 | 1 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/src/Banijay_pipeline/creating_fragments.ipynb | At first, I was using the wrong function and it was causing errors.
| Done | Max 4 hours tasks | Converting speech into text | Programming | ILO 4.2 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/src/Banijay_pipeline/Speach_to_text.ipynb | Openai didn't work for me that why i use different library
| Done | Max 4 hours tasks | Converting speech into text using speech_recognition | Programming | ILO 4.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/src/Banijay_pipeline/Speach_to_text.ipynb
| Done | Max 4 hours tasks | Creating new submision for individual kaggle chelenge. | Programming | ILO 4.2 | 2 | 2.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/src/Banijay_pipeline/Speach_to_text.ipynb | I used new data set. And got score 0.921
| Done | Max 4 hours tasks | Creating first transformer model with multiclases | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transfer%20learning%20models
| Done | Max 4 hours tasks | Preparing for the feedback Sesion | Evidencing | ILO 1.0 | 1 | 1 | 0
| Done | Max 4 hours tasks | Reserch about transformer model | Research | ILO 4.2 | 3 | 3 | 0
| Done | Max 4 hours tasks | Testing transformers models for multiclases | Programming | ILO 4.2 | 3 | 2.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transformer%20models
| Done | Max 4 hours tasks | Creating first Kaggle submission with transformer model for group challenge | Programming | ILO 4.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transformer%20models
| Done | Max 4 hours tasks | Fixing an error when converting speech to text | Programming | ILO 4.2 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Text_to_speach | Problem was that some fragments were to long
| Done | Max 4 hours tasks | Preparing model for training on bigger data set | Programming | ILO 4.2 | 2 | 2 | 0
| Done | Max 4 hours tasks | Preparing data set for training | Programming | ILO 4.2 | 2 | 2 | 0
| Done | Max 4 hours tasks | Analising results from model | Study | ILO 4.2 | 2 | 2 | 0 |  | Model trained on 200 000 rows performed worst than this trained on 1000 rows
| Done | Max 4 hours tasks | Searching for solutions how to improve kaggle score | Research | ILO 5.0 | 4 | 4 | 0
|  |  |  | Total Hours |  | 35.5 | 36.75 | 1.25
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Generate data for transformer model | Programming |  | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Datasets/generated%20data
| Done | Max 4 hours tasks | Adjusting generated data | Programming |  | 3 | 3.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Datasets/generated%20data
| Done | Max 4 hours tasks | Generative AI selfstudy | Study |  | 4 | 4.5 | 0.5
| Done | Max 4 hours tasks | Sesting generated data on Transforemer model | Programming | ILO 4.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transformer%20models
| Done | Max 4 hours tasks | Reserch about transformer model | Research | ILO 4.2 | 3 | 2.5 | -0.5 |  | I search for better model
| Done | Max 4 hours tasks | Applying large bret model | Programming |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transformer%20models
| Done | Max 4 hours tasks | Improving submiosion score on group kaggle. | Programming | ILO 5.0 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Transformer%20models | I was testing diferent trainig parameters.
| Done | Max 4 hours tasks | Adjusting LTSM model | Programming | ILO 4.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/Statistical%20%26%20Neural%20Models
| Done | Max 4 hours tasks | task 6 TF-IDF | Programming | ILO 4.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-DominikSzewczyk224180/tree/main/Natural%20Language%20procesing/TF-IDF
| Done | Max 4 hours tasks | Describing models | Evidencing |  | 3 | 3 | 0 |  | Kaggle form
| Done | Max 4 hours tasks | Starting with Report (Data procesing and exploration) | Study | ILO 6.0 | 2 | 2 | 0 | https://www.overleaf.com/project/65fc621ae9c36a4a80f941fd
| Done | Max 4 hours tasks | Research about datasets | Research | ILO 6.0 | 4 | 4 | 0
| Done | Max 4 hours tasks | Writin Data procesing and exploration secion | Study | ILO 6.0 | 3 | 3.5 | 0.5 | https://www.overleaf.com/project/65fc621ae9c36a4a80f941fd
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 38 | 38.25 | 0.25
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
| Done | Max 4 hours tasks | Team meeting | Meeting | ILO 3.0 | 4 | 4 | 0 |  | Discussing finalization of the project and presentation.
| Done | Max 4 hours tasks | Preparing a presentation | Study | ILO 3.0 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Visialising Data distribution (secion in the report and presentation) | Study | ILO 6.0 | 3 | 2.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Adjusting slides on the presentation | Study | ILO 3.0 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Preparing for presentation, creating notes and practising. | Study | ILO 3.0 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Team meeting practise presenting | Meeting | ILO 3.0 | 1 | 1.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Team meeting practise presenting 2 | Meeting | ILO 3.0 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Final presentation | Meeting | ILO 3.0 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Presentation_group2.pptx
| Done | Max 4 hours tasks | Lats changes in the report (checking grammar etc) | Study | ILO 6.0 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24c-fai2-adsai-group-group2/blob/main/deliverables/Technical_Report_group2.pdf
| Done | Max 4 hours tasks | Preparing all files, tasks and folders for final evidencing | Evidencing |  | 4 | 4 | 0
| Done | Max 4 hours tasks | Learning log Secion C | Evidencing |  | 4 | 4.5 | 0.5
| Done | Max 4 hours tasks | Learning log Secion D | Evidencing |  | 3 | 3 | 0
|  |  |  | Total Hours |  | 29 | 30.25 | 1.25

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.0 | W1: 0 | 0
ILO 2.0 | [8 empty] | 0
ILO 3.0 | [8 empty] | 0
ILO 4.1 | [8 empty] | 0
ILO 4.2 | [8 empty] | 0
ILO 5.0 | [8 empty] | 0
ILO 6.0 | [8 empty] | 0
NA | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.0
Unplanned | Meeting | ILO 2.0 | Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!
Blocked | Programming | ILO 3.0
In-Progress | Research | ILO 4.1
Done | Testing | ILO 4.2
Delayed | Workshop | ILO 5.0
Cancelled | Planning | ILO 6.0
| Evidencing | NA
Debugging
Lecture
Study
Unplanned
Distraction
Break