## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | new team we have to get to know each otehrs
2024-05-06 | Done | Max 4 hours tasks | First look on the creative brief | Research | ILO 1.1 | 2 | 2 | 0
2024-05-06 | Done | Max 4 hours tasks | Creating a team | Meeting |  | 1 | 0.5 | -0.5
2024-05-06 | Done | Max 4 hours tasks | Kick-off | Lecture |  | 1 | 1 | 0
2024-05-06 | Done | Max 4 hours tasks | First team meating | Meeting | ILO 2.1 | 1 | 1.5 | 0.5 |  | We exchanged our strengths and told how we see our role in the project
2024-05-06 | Done | Max 4 hours tasks | Reviewing ilos with team | Meeting | ILO 1.1 | 3 | 3 | 0
2024-05-07 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-07 | Done | Max 4 hours tasks | Intro to MLOps (Machine Learning Operations) | Study | ILO 4.1 | 1 | 1 | 0
2024-05-07 | Done | Max 4 hours tasks | MLOps for Business on DataCamp | Study | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/MLOps%20for%20Business_certificate.pdf
2024-05-07 | Done | Max 4 hours tasks | MLOps Essentials: Model Development and Integration on LinkedIn Learning | Study | ILO 4.1 | 2 | 1.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/CertificateOfCompletion_MLOps%20Essentials%20Model%20Development%20and%20Integration.pdf
2024-05-07 | Done | Max 4 hours tasks | Git and GitHub Best Practices for collaboration | Study |  | 2 | 1.75 | -0.25
2024-05-08 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-08 | Done | Max 4 hours tasks | Meeting with product owner | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-05-08 | Done | Max 4 hours tasks | Working with Azure Devops | Study | ILO 4.1 | 2 | 2 | 0
2024-05-08 | Done | Max 4 hours tasks | Planing tasks with team | Meeting | ILO 1.1 | 1 | 1 | 0
2024-05-08 | Done | Max 4 hours tasks | Preparing presentation of Block B results | Evidencing | ILO 1.1 | 1 | 1 | 0
2024-05-08 | Done | Max 4 hours tasks | Shearing ideas around team about Block b project | Meeting |  | 2 | 2 | 0
2024-05-08 | Done | Max 4 hours tasks | Meeting with product owner | Meeting |  | 0.25 | 0.25 | 0
2024-05-09 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-09 | Done | Max 4 hours tasks | Organizing ML/DS Project | Study | ILO 4.1 | 1 | 1 | 0
2024-05-09 | Done | Max 4 hours tasks | Project Folder Structure | Design | ILO 1.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/CV1
2024-05-09 | Done | Max 4 hours tasks | Basic MNIST Example of Notebook to Package (almost) | Programming |  | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/mnist_project
2024-05-09 | Done | Max 4 hours tasks | MLOps Maturity Levels - Article from MS Azure ML Accelerator | Study | ILO 4.1 | 1 | 1 | 0
2024-05-09 | Done | Max 4 hours tasks | Seting up poetry | Programming |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/CV1/pyproject.toml | i encountered some errors with python version ect.
2024-05-10 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-10 | Done | Max 4 hours tasks | Labeling images to increase data set | Design |  | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/CV1/data/raw/NPEC/to_mask/Dominik
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 34.75 | 35.25 | 0.5
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | We have ot creat a pottry and work wit hte same package versions
2024-05-13 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-13 | Done | Max 4 hours tasks | Sprint Review | Meeting | ILO 1.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-13 | Done | Max 4 hours tasks | Sprint Retrospective | Meeting | ILO 1.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-13 | Done | Max 4 hours tasks | Preparing Tasks for sprint planing | Study | ILO 1.1 | 1 | 1.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-13 | Done | Max 4 hours tasks | Sprint Planning | Planning | ILO 1.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-13 | Done | Max 4 hours tasks | Self study about Azure Devops | Study |  | 1 | 1 | 0
2024-05-14 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-14 | Done | Max 4 hours tasks | Estimate Story points for every task | Meeting | ILO 1.1 | 1 | 1.5 | 0.5 |  | It was harder than we expect, tasks werent well described
2024-05-14 | Done | Max 4 hours tasks | Reviewing data preprocessing | Programming |  | 1 | 1 | 0
2024-05-14 | Done | Max 4 hours tasks | Client-side Continuous Integration Tools with Python | Study |  | 2 | 1.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/.pre-commit-config.yaml
2024-05-14 | Done | Max 4 hours tasks | Reviewing how Branches on github works | Study |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/.pre-commit-config.yaml
2024-05-14 | Done | Max 4 hours tasks | Implementing Continuous Integration Tools | Programming |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/.pre-commit-config.yaml
2024-05-14 | Done | Max 4 hours tasks | Testing Continuous Integration Tools | Testing |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/.pre-commit-config.yaml | It causes many errors i had to solve
2024-05-15 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-15 | Done | Max 4 hours tasks | Research about Neurodrive | Research |  | 0.5 | 0.5 | 0
2024-05-15 | Done | Max 4 hours tasks | Daria Zhigulskaya the CEO of Neurodrive use of data science and biotelemetry in sports | Lecture |  | 1.5 | 1.5 | 0 |  | One of the best guest lecture we had
2024-05-15 | Done | Max 4 hours tasks | Setting up poetry (finding the best python and tf version) | Programming |  | 4 | 5 | 1 |  | The last thing we did to resolve the errors was to allow the system to make longer calls (I think that says a lot about how complicated the process was)
2024-05-16 | Done | Max 4 hours tasks | Stand up meeting | Meeting |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-16 | Done | Max 4 hours tasks | Testing U-net model | Programming | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/notebooks/DS_U-net_model.ipynb
2024-05-16 | Done | Max 4 hours tasks | implementing U-net model to our case | Programming | ILO 4.1 | 3 | 2.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/notebooks/DS_U-net_model.ipynb
2024-05-16 | Done | Max 4 hours tasks | Set-up version control and documentation | Programming |  | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/notebooks/DS_setup_version_control_and_documentation.ipynb
2024-05-16 | Done | Max 4 hours tasks | Team building execises (spring festival) | Meeting |  | 4 | 4 | 0
2024-05-17 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-17 | Done | Max 4 hours tasks | Set-up version control and documentation | Programming |  | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/notebooks/DS_setup_version_control_and_documentation.ipynb
2024-05-17 | Done | Max 4 hours tasks | Testning transformer model for CV | Programming | ILO 4.1 | 3 | 3.5 | 0.5
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 37 | 38.75 | 1.75
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | Working with 3 teammets becaous 2 team mates are in viena, we have to worke a bit more.
2024-05-20 | Done | Max 4 hours tasks | Testning transformer model for CV | Programming | ILO 4.1 | 4 | 4 | 0 |  | i tested DETR, SegFormer and Mask2Former
2024-05-20 | Done | Max 4 hours tasks | Research about transformer model for CV | Research | ILO 4.1 | 3 | 2.75 | -0.25 | https://www.youtube.com/watch?v=xuh37qziXnw&pp=ygUNZGVydCBhaSBtb2RlbA%3D%3D | hugging face\ YT
2024-05-21 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-21 | Done | Max 4 hours tasks | Adjusting set-up version control and documentation | Programming |  | 2 | 2.5 | 0.5 |  | I automated funcions
2024-05-21 | Done | Max 4 hours tasks | Reviuing knowlage about unit testing | Study | ILO 3.1 | 2 | 2 | 0
2024-05-21 | Done | Max 4 hours tasks | Unit testing for version control and documentation | Programming | ILO 3.1 | 4 | 3.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/tests/test_model_saving.py
2024-05-22 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-22 | Done | Max 4 hours tasks | Adjusting unit testing to pass pre-commit hooks | Programming |  | 2 | 2.5 | 0.5
2024-05-22 | Done | Max 4 hours tasks | Start working on inference pipeline (folder structure and functions planning) | Planning | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-22 | Done | Max 4 hours tasks | predict_masks funion in inference pipeline | Programming | ILO 3.1 | 2 | 2.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-22 | Done | Max 4 hours tasks | Automating predict_masks funcion | Programming | ILO 3.1 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-23 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-23 | Done | Max 4 hours tasks | Automated funion to visualise masks | Programming | ILO 3.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-23 | Done | Max 4 hours tasks | Testing mask procesing functions from BlockB | Programming | ILO 3.1 | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference | Functions didn't work corectly
2024-05-23 | Done | Max 4 hours tasks | Creating new procesing funcion | Programming | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-23 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-24 | Done | Max 4 hours tasks | Adjusting preprocesing funion to work with Landmarks Detecion | Programming |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-24 | Done | Max 4 hours tasks | Landmarks Detecion Funcion | Programming | ILO 3.1 | 3 | 3.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-24 | Done | Max 4 hours tasks | Finalising Inference pipeline | Programming | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/scr/Inference
2024-05-24 | Done | Max 4 hours tasks | Planing tasks for next sprint | Planning |  | 2 | 2 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 39 | 40.75 | 1.75
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | Working with 3 teammets becaous 2 team mates are in viena, we have to worke a bit more.
2024-05-27 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-27 | Done | Max 4 hours tasks | Sprint Review | Meeting | ILO 1.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-27 | Done | Max 4 hours tasks | Sprint Retrospective | Meeting | ILO 1.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-27 | Done | Max 4 hours tasks | Preparing Tasks for sprint planing | Study | ILO 1.1 | 2 | 2.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md | As a scrum master i had more to do than usual
2024-05-27 | Done | Max 4 hours tasks | Sprint Planning | Planning | ILO 1.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-27 | Done | Max 4 hours tasks | Cleaning azure board | Planning | ILO 1.1 | 3 | 3 | 0 | https://dev.azure.com/2024-ADSAI-Y2D/CV1%20-%20Dean/_boards/board/t/CV1%20-%20Dean%20Team/Issues
2024-05-28 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0
2024-05-28 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-28 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-28 | Done | Max 4 hours tasks | Unit testing for model_saving | Programming | ILO 3.2 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/tests/test_model_saving.py
2024-05-28 | Done | Max 4 hours tasks | Type hinting for model_saving | Programming | ILO 3.2 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/models/model_saving.py
2024-05-28 | Done | Max 4 hours tasks | Logging for model_saving | Programming | ILO 3.2 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/models/model_saving.py
2024-05-28 | Done | Max 4 hours tasks | Sphinx documentation for model_saving | Programming | ILO 3.2 | 2 | 2.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs
2024-05-28 | Done | Max 4 hours tasks | Seting up sphinx documetation | Programming | ILO 3.2 | 2 | 3 | 1 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs | I had some errors and i decided to solve them on datalabs.
2024-05-29 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-29 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-29 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-29 | Done | Max 4 hours tasks | Solving problems with sphinx | Debugging | ILO 3.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs
2024-05-29 | Done | Max 4 hours tasks | Designing sphinx site | Programming |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs
2024-05-29 | Done | Max 4 hours tasks | Solving problems with potry | Debugging |  | 2 | 3 | 1 |  | I had to reinstall everything
2024-05-29 | Done | Max 4 hours tasks | Structuring Readme.md file | Design | ILO 3.2 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/README.md
2024-05-30 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-30 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-30 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-30 | Done | Max 4 hours tasks | Introduction to Cloud Computing | Study | ILO 4.1 | 3 | 3 | 0
2024-05-30 | Done | Max 4 hours tasks | Understanding Cloud Computing course | Study | ILO 4.1 | 2 | 1.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Understanding%20Cloud%20Computing.pdf
2024-05-30 | Done | Max 4 hours tasks | Microsoft Azure Machine Learning | Study | ILO 4.1 | 2 | 2 | 0
2024-05-31 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-31 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-31 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-05-31 | Done | Max 4 hours tasks | Explore developer tools for workspace interaction course | Study |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Explore%20developer%20tools%20for%20workspace%20interaction.png
2024-05-31 | Done | Max 4 hours tasks | Introduction to Azure Machine Learning course | Study | ILO 4.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Introduction%20to%20Azure%20Machine%20Learning.png
2024-05-31 | Done | Max 4 hours tasks | Learning workspace resources and assets course | Study | ILO 4.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Learning%20workspace%20resources%20and%20assets.png
2024-05-31 | Done | Max 4 hours tasks | Make data available in Azure Machine Learning course | Study | ILO 4.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Make%20data%20available%20in%20Azure%20Machine%20Learning.png
2024-05-31 | Done | Max 4 hours tasks | Work with compute targets in Azure Machine Learning course | Study | ILO 4.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Work%20with%20compute%20targets%20in%20Azure%20Machine%20Learning.png
2024-05-31 | Done | Max 4 hours tasks | Work with data in Azure Machine Learning course | Study | ILO 4.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Work%20with%20data%20in%20Azure%20Machine%20Learning.png
2024-05-31 | Done | Max 4 hours tasks | Work with environments in Azure Machine Learning course | Study | ILO 3.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Work%20with%20environments%20in%20Azure%20Machine%20Learning.png
| Done | Max 4 hours tasks | Connecting Azure workspace to our repo | Study | ILO 4.1 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/utils/configuration.py
| Done | Max 4 hours tasks | Register the Environment | Programming | ILO 3.1 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/utils/register_environment.py
| Done | Max 4 hours tasks | Verify enviroment registration | Programming | ILO 3.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/utils/verify_environment.py
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 43.5 | 44 | 0.5
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | Pipeline still need improvment
2024-06-03 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-03 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-03 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-03 | Done | Max 4 hours tasks | Buildning enviroment in the cloud | Programming | ILO 3.1 | 2 | 2 | 0
2024-06-03 | Done | Max 4 hours tasks | Solving errors with enviroment in the cloud | Programming | ILO 3.1 | 3 | 3.25 | 0.25 |  | The problem was that the environment name was incorrect…..
2024-06-04 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-04 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-04 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-04 | Done | Max 4 hours tasks | Testing enviroment | Programming | ILO 3.1 | 4 | 3.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/utils/test_enviroment_train.py
2024-06-04 | Done | Max 4 hours tasks | Seting up sphinx documentation, (selfstudy) | Study | ILO 3.2 | 2 | 2 | 0
2024-06-05 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-05 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-05 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-05 | Done | Max 4 hours tasks | Seting up sphinx documetation website | Programming | ILO 3.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs
2024-06-05 | Done | Max 4 hours tasks | Changing the theme of the Sfinks website | Design | ILO 3.2 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs
2024-06-05 | Done | Max 4 hours tasks | Structuring sphinx website | Design |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/main/ATHENA/docs
2024-06-06 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-06 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-06 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-06 | Done | Max 4 hours tasks | Uploading sphinx website to the github pages | Programming |  | 3 | 3.5 | 0.5
2024-06-06 | Done | Max 4 hours tasks | Adjusting sphinx set up and style to work with github | Programming |  | 3 | 2.75 | -0.25
2024-06-07 | Done | Max 4 hours tasks | Preparation for Stand up meeting | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-07 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-07 | Done | Max 4 hours tasks | Describing stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-07 | Done | Max 4 hours tasks | Unit testing for visualisation.py | Programming | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/Inference/visualization.py
2024-06-07 | Done | Max 4 hours tasks | Type hinting for model_saving visualisation.py | Programming | ILO 3.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/Inference/visualization.py
2024-06-07 | Done | Max 4 hours tasks | Logging for model_saving visualisation.py | Programming | ILO 3.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/Inference/visualization.py
2024-06-07 | Done | Max 4 hours tasks | Sphinx documentation for model_saving visualisation.py | Programming | ILO 3.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/scr/Inference/visualization.py
| Done | Max 4 hours tasks | Self study and research about tracking costs expectations | Research | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/Training_cost_expectations.md
| Done | Max 4 hours tasks | Tracking costs expectations | Evidencing | ILO 4.1 | 3 | 3.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/ATHENA/Training_cost_expectations.md
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 41.5 | 41.75 | 0.25
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | ApI Is a new for us thats why i have to focus more on self study
2024-06-10 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-10 | Done | Max 4 hours tasks | Preparing for Sprint Review | Meeting | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-10 | Done | Max 4 hours tasks | Sprint Review | Meeting | ILO 1.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md | It's great feeling to hear positive feedback after trying my best for the past 2 weeks as a scrum master
2024-06-10 | Done | Max 4 hours tasks | Sprint Retrospective | Study | ILO 1.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-10 | Done | Max 4 hours tasks | Describing Sprint Retrospective | Evidencing | ILO 1.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-10 | Done | Max 4 hours tasks | Preparing Tasks for sprint planing | Study | ILO 1.1 | 1 | 0.75 | -0.25
2024-06-10 | Done | Max 4 hours tasks | Sprint Planning | Planning | ILO 1.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-10 | Done | Max 4 hours tasks | Starting with Advanced GitHub Techniques (CI/CD) self study | Study |  | 2 | 2.5 | 0.5
2024-06-11 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-11 | Done | Max 4 hours tasks | Azure Machine Learning III - Deploying Models self-study | Study | ILO 4.1 | 3 | 3.5 | 0.5 |  | it was harder than i expected
2024-06-11 | Done | Max 4 hours tasks | Application Programming Interfaces (APIs) self study | Study | ILO 5.1 | 3 | 4 | 1 |  | Creating a more complex API couses some unexpected problems
2024-06-12 | Done | Max 4 hours tasks | Stand up meeting | Meeting |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-12 | Done | Max 4 hours tasks | Review Session 1 (azure ml) | Lecture | ILO 4.1 | 2 | 2 | 0
2024-06-12 | Done | Max 4 hours tasks | Uplouding data to the cloud | Programming | ILO 4.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/Cloud
2024-06-12 | Done | Max 4 hours tasks | Creating data assets | Programming | ILO 4.1 | 1.5 | 1.75 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/Cloud
2024-06-12 | Done | Max 4 hours tasks | Reviuing Review Session 1 (azure ml) | Study |  | 2 | 2 | 0
2024-06-12 | Done | Max 4 hours tasks | Runing first job on azure ml | Programming |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/Cloud
2024-06-13 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-13 | Done | Max 4 hours tasks | Building pipeline to run it in the cloud | Programming |  | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/Cloud | It was way harder that i expected and i wasnt able to finish it
2024-06-13 | Done | Max 4 hours tasks | Application Programming Interfaces (APIs) self study | Study |  | 2 | 2 | 0
2024-06-13 | Done | Max 4 hours tasks | Starting building API | Programming | ILO 5.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/development/app
2024-06-14 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-14 | Done | Max 4 hours tasks | Building API for feedback-loop | Programming | ILO 5.1 | 3 | 2.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/development/app
2024-06-14 | Done | Max 4 hours tasks | Adding aditional features for API feedback-loop | Programming | ILO 5.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/development/app
2024-06-14 | Done | Max 4 hours tasks | Testing API feedback-loop | Testing | ILO 5.1 | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 36.5 | 38 | 1.5
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | Docekrs are a new for us thats why i have to focus more on self study
2024-06-17 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-17 | Done | Max 4 hours tasks | Discusing API with team | Meeting | ILO 2.1 | 1 | 1 | 0
2024-06-17 | Done | Max 4 hours tasks | Review Session 2 (azure ml) | Lecture |  | 2 | 2 | 0
2024-06-17 | Done | Max 4 hours tasks | Reviuing Review Session 2 (azure ml) | Study |  | 1.5 | 1.75 | 0.25
2024-06-17 | Done | Max 4 hours tasks | Meeting with product owner (Dean) | Meeting |  | 0.5 | 0.5 | 0
2024-06-17 | Done | Max 4 hours tasks | Runing pipeline in the clound (on azure ml as a job) | Programming | ILO 4.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/Cloud | Job was constantly running (error)
2024-06-18 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-18 | Done | Max 4 hours tasks | Containerisation with Docker | Study | ILO 5.1 | 3 | 3 | 0
2024-06-18 | Done | Max 4 hours tasks | Introduction to Docker | Study | ILO 5.1 | 4 | 5 | 1 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/blob/main/Slef-study/Course%20Dockers.png | Course was way harder than i expected
2024-06-18 | Done | Max 4 hours tasks | Review of docker image for backend | Testing | ILO 5.1 | 1 | 2 | 1 |  | i had to change some code because image wasn't building correctly
2024-06-19 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-19 | Done | Max 4 hours tasks | Discusing folder structure | Meeting | ILO 2.1 | 0.5 | 0.5 | 0
2024-06-19 | Done | Max 4 hours tasks | Planing tasks next 10 days (team) | Meeting | ILO 1.1 | 1 | 1 | 0
2024-06-19 | Done | Max 4 hours tasks | Implementing changes from review sesion to pipeline (GPU ect) | Programming |  | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-DominikSzewczyk224180/tree/main/Cloud
2024-06-19 | Done | Max 4 hours tasks | Meeting with product owner (Dean) | Meeting | ILO 2.1 | 0.5 | 0.5 | 0
2024-06-19 | Done | Max 4 hours tasks | Creating a docker image for frontend | Programming |  | 2 | 2.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/Dokers/app/frontend/Dockerfile
2024-06-20 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0
2024-06-20 | Done | Max 4 hours tasks | Deployment Options and Strategies | Study |  | 2 | 1.5 | -0.5
2024-06-20 | Done | Max 4 hours tasks | Finishing the docker image for frontend | Programming | ILO 5.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/Dokers/app/frontend/Dockerfile
2024-06-20 | Done | Max 4 hours tasks | Runing a docker conteiner for fronend | Programming | ILO 5.1 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/Dokers/app/frontend/Dockerfile
2024-06-20 | Done | Max 4 hours tasks | Creating docker-compose.ym | Programming | ILO 5.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/Dokers/app/docker-compose.yml
2024-06-20 | Done | Max 4 hours tasks | Automaring the frontend docker | Programming | ILO 5.1 | 1 | 2 | 1 |  | I coudnt creat a git hub secret
2024-06-21 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-21 | Done | Max 4 hours tasks | Format file structure to prepare it for sphinx documetation | Planning | ILO 3.2 | 1 | 1 | 0
2024-06-21 | Done | Max 4 hours tasks | Finalising and testing auto daploy frontend and backend | Programming | ILO 5.1 | 3 | 3 | 0
2024-06-21 | Done | Max 4 hours tasks | Secion C learning log | Evidencing |  | 4 | 4 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 40.5 | 42.75 | 2.25 | s
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | Unit tests are not ready yet we have to work on them more
2024-06-24 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-24 | Done | Max 4 hours tasks | Sprint Review | Meeting | ILO 1.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-24 | Done | Max 4 hours tasks | Sprint Retrospective | Meeting | ILO 1.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-24 | Done | Max 4 hours tasks | Preparing Tasks for sprint planing | Study | ILO 1.1 | 1 | 1.25 | 0.25
2024-06-24 | Done | Max 4 hours tasks | Sprint Planning | Planning | ILO 1.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-24 | Done | Max 4 hours tasks | Helping with improving unit testing to get 85% coverage | Programming | ILO 3.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/test/app/backend/ATHENA/scr/unittests
2024-06-24 | Done | Max 4 hours tasks | Sphinx Documetation based on new folder structure | Programming |  | 2 | 2 | 0
2024-06-25 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-25 | Done | Max 4 hours tasks | Descripon for Sphinx documetation | Evidencing | ILO 3.2 | 2 | 2.25 | 0.25
2024-06-25 | Done | Max 4 hours tasks | Adding Sphinx to the git hub pages | Programming | ILO 3.2 | 3 | 2.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/Sphinx_2.0/app/backend/ATHENA/docs
2024-06-25 | Done | Max 4 hours tasks | Adjusting Training costs expectations | Programming | ILO 4.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/test/Management/Training_cost_expectations.md
2024-06-26 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-26 | Done | Max 4 hours tasks | Serching for the error in the pipeline (runing in the cloud) | Programming | ILO 4.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/test/app/backend/ATHENA/scr/pipeline.py | Finally i found out that error is during loading the data
2024-06-26 | Done | Max 4 hours tasks | Solving an error in the pipeline (runing in the cloud) | Programming | ILO 4.1 | 2 | 3.5 | 1.5 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/test/app/backend/ATHENA/scr/pipeline.py | It didn't want to work, I tested different data assets without success but finally, we managed by rewriting the data loading function.
2024-06-26 | Done | Max 4 hours tasks | Discusing errors with team and sloving them (folder strusctures preprocesing scr) | Meeting | ILO 2.1 | 2 | 2 | 0
2024-06-26 | Done | Max 4 hours tasks | Improving API (feedback loop implemetation) | Programming | ILO 5.1 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/test/app/backend
2024-06-27 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-27 | Done | Max 4 hours tasks | Runing pipeline in the clound (on azure ml as my job) | Programming | ILO 4.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/test/app/backend/ATHENA/scr/pipeline.py
2024-06-27 | Done | Max 4 hours tasks | Adding ilos to worklog and lerning log | Evidencing |  | 2 | 2.25 | 0.25
2024-06-27 | Done | Max 4 hours tasks | Learning log section D | Evidencing |  | 2 | 1.5 | -0.5
2024-06-27 | Done | Max 4 hours tasks | Learning log section C (1,2,3) | Evidencing |  | 3 | 3 | 0
2024-06-27 | Done | Max 4 hours tasks | Meeting with a team, discusing evidencing | Evidencing |  | 0.5 | 0.5 | 0
2024-06-27 | Done | Max 4 hours tasks | Learning log section C (4,5) | Evidencing |  | 2 | 1.5 | -0.5
2024-06-27 | Done | Max 4 hours tasks | Unit test for everything where it is missing just to have 85% of coverage | Programming | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/test/app/backend/ATHENA/scr/unittests
2024-06-28 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/blob/main/Management/Stand-Ups.md
2024-06-29 | Done | Max 4 hours tasks | Unit test for everything where it is missing just to have 85% of coverage | Programming | ILO 3.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24d-fai2-adsai-group-cv1/tree/test/app/backend/ATHENA/scr/unittests
2024-06-29 | Done | Max 4 hours tasks | Final touches to the project, discussing presentation with team | Meeting | ILO 2.1 | 1 | 1 | 0
2024-06-29 | Done | Max 4 hours tasks | Finall presentation | Workshop |  | 3 | 3 | 0
2024-06-29 |  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 47.5 | 48 | 0.5

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.1 | W1: 0 | 0
ILO 1.2 | [8 empty] | 0
ILO 2.1 | [8 empty] | 0
ILO 3.1 | [8 empty] | 0
ILO 3.2 | [8 empty] | 0
ILO 4.1 | [8 empty] | 0
ILO 5.1 | [8 empty] | 0
ILO 6.2 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.1
Unplanned | Meeting | ILO 1.2 | Don't touch this sheet! This sheet is not relevant for you this year! It becomes relevant when you set your own Intended Learning Outcomes (ILO)!
Blocked | Programming | ILO 2.1
In-Progress | Research | ILO 3.1
Done | Testing | ILO 3.2
Delayed | Workshop | ILO 4.1
Cancelled | Planning | ILO 5.1
| Evidencing | ILO 6.2
Debugging
Lecture
Study
Unplanned
Distraction
Break